## Sheet1
Year | Quarter | Week | Continuous Integration | Continuous Delivery | Development and Administration | Time
2021 | Q4 | 2021-10-17 |  |  | Review Project Specifications Create local development environment Setup Azure Account | 3 hr
|  | 2021-10-24 | Create Github Repo |  | Create Trello and Tracking Spreadsheet | 4 hr
|  | 2021-10-31 | Create Project Scaffolding Setup Github Actions |  |  | 2 hr
|  | 2021-11-07 |  | Create Azure Web app Setup AzureDevops Account Create Azure Github Pipeline |  | 4 hr
|  | 2021-11-14 |  | Integrate Fask ML App into project |  | 5 hr
|  | 2021-11-21 |  |  | Implement Locust to perform load testing | 1 hr
|  | 2021-11-28 |  |  | Complete Documentation | 4 hr
|  | 2021-12-05 |  |  | Complete Demo Video | 6 hr
|  | 2021-12-19 |  |  | Submit for review Respond to feedback | 3 hr
2022 | Q1 | 2022-01-02 |  |  | Create upgrade/additions plan | 2 hr
|  | 2022-01-09 | Write additional tests |  | Pefrform front-end coding | 40 hr
|  | 2022-01-16 | Write additional tests |  | Perform back-end coding | 40 hr
|  | 2022-01-23 |  |  | Test New Features Demo updated application | 40 hr
|  |  | Goals | Goals | Goals
|  |  | Setup automated testing/linting | Create pipelines to ensure efficient code delivery | Create Project Plan
Create Development Environment
Document Project
Create long-term plan and strategy
Deliver proper functioning and useful web application